## Start Here
CONSTRUCTION CALCULATOR - INDIA
Plan, estimate and track your build or renovation. Yellow cells are for you to fill in. Green cells calculate automatically.
EXAMPLE PROJECT: 30 x 50 ft plan with sample numbers and sample rates. Use the blank master file for your own project.
START IN 5 STEPS
Step | Where | What to do
1 | Quick Start | Answer the six questions: project name, client, built-up area, budget, city, and Feet or Metres.
2 | Rates | Type in your local rates. Costs stay at zero until you do.
3 | Room Area to Steel | Enter room sizes, openings and quantities in the yellow boxes.
4 | Cost Estimate | Add costs for items the calculators don't cover. Tag each one with a stage.
5 | Order List and Stage Budget | Use the Order List to buy materials, and the Stage Budget to check money stage by stage.
WHAT'S INSIDE
Tab | What it does
Quick Start | Six answers to start: name, client, area, budget, city, and Feet or Metres.
Assumptions | Every factor the calculations use, with where to change it and its source status.
Terms & Disclaimer | What this file is, what it is not, and what remains to be completed before sale.
Setup | Project type, contingency and GST. Name, area, budget and units come from Quick Start.
Room Area | Floor area of each room, in sq ft and sq m.
Earthwork | Volume of soil to dig for foundations, trenches and pits, with cost.
Paint & Tiles | Paint litres and tile count, totalled for every room.
Exterior & Roof | Outside wall paint and flat roof waterproofing, with labour.
Room Costs | Paint and tile cost for each room, with each room's share.
Concrete | Concrete volume, cement, sand and aggregate quantities, and cost.
Bricks & Blocks | Brick count, AAC block count and masonry labour.
Plaster | Plaster cement, sand and cost for walls and ceilings.
Services | Count of plumbing and electrical points, with cost per point.
Steel | Steel weight from bar size and number of bars.
Cost Estimate | Full estimate, with contingency, GST and actual spend.
Stage Budget | Estimate and actual spend for each stage, against your target.
Stage Checklist | Checks to tick off before moving to the next stage.
Order List | Materials to buy, with wastage, supplier and order-by date.
Task Tracker | Tasks by stage and room, with who does them, due dates and overdue flags.
Permits | Approvals and permits to apply for, with status and dates.
Rates | Your local rates. Used by every calculator.
Rate Quotes | Compare two supplier quotes and copy the lower rate to Rates.
Dashboard | Charts and key numbers for the whole project.
Bill Check | Compare a contractor's claimed quantities with your calculations.
Projects | Track up to five projects in one file.
Bids | Compare up to three contractor quotes per job.
Payments | Record payments and change orders, and see the balance still to pay.
Timeline | Task schedule with dates, progress and days left.
Quotation | Printable quotation for your client.
Rate Library | Keep supplier rates by city and copy them to Rates.
IMPORTANT
- These are estimates for planning. They are not a structural design. Have a qualified engineer check the design and quantities.
- Rates, wastage and coverage vary by supplier and site. Replace the blank rates with your own quotes before relying on the totals.
- Sheets are protected with no password. To change a formula: Review > Unprotect Sheet.
- Costs appear only after you enter rates on the Rates tab. Until then, every cost shows zero.
- Changing Units does not convert numbers you have already typed. Re-enter them after switching.
- This file does NOT calculate: plumbing and electrical quantities, the price of doors and windows, external wall painting, waterproofing area, roofing, labour for tiles and paint, transport, approval fees, backfilling and soil removal. Enter these by hand or get quotes.
- Paint is calculated on walls only. Ceilings are not painted in the calculation. Add ceiling paint under Other.
- The estimate uses the brick option only. AAC blocks are calculated on the Bricks & Blocks tab but are not in the Cost Estimate. Choose one or the other.
- Tested in LibreOffice only. Not yet tested in Microsoft Excel or Google Sheets.
- The Assumptions tab lists every factor the calculations use. The Terms tab sets out what the file is and is not. Read both before relying on any figure.

## Quick Start
QUICK START
Answer these six questions first. The rest of the file uses your answers.
EXAMPLE: placeholder rates and quantities. These totals are NOT a real estimate.
Question | Your answer | Why we need it
Project name | My Home Project | Shown on every tab and on the quotation
Client / owner |  | Shown on the quotation
Built-up area | 1500 | Total floor area of the building, in the units you choose below
Target budget (₹) | 2500000 | The most you plan to spend
City | Chennai | For your reference
Units | Feet | Feet or Metres. Set this before you measure anything. Changing it does not convert numbers already typed.
THEN WORK THROUGH THESE TABS IN ORDER
Step | Tab | What to do
1 | Room Area | Enter each room's size.
2 | Paint & Tiles | Enter each room once, with its doors and windows.
3 | Concrete | Enter slabs, beams, columns and footings. Use the mix your engineer specifies.
4 | Bricks & Blocks | Enter wall lengths, heights and openings.
5 | Steel | Enter bar sizes and counts from your structural drawings.
6 | Rates | Type in your own quotes. Costs show as zero until you do.
7 | Cost Estimate | Add costs the calculators don't cover, and tag each with a stage.
8 | Stage Budget and Order List | Check spend by stage and see what to buy.
Yellow cells are yours to change. Green cells calculate automatically.

## Setup
SETUP
Enter this once for each project. Every calculator uses these settings.
EXAMPLE: placeholder rates and quantities. These totals are NOT a real estimate.
Setting | Your entry | What to enter
Project name | EXAMPLE: 3 bedroom house, 30 x 50 ft plan, Chennai | Any name you like
Client / owner | Sample client | Name of the homeowner or client (used on the quotation)
City | Chennai | For your reference
Project type | New build | For your reference. It doesn't change calculations.
Units |  | Feet or Metres. Set this before you measure anything. Changing it does not convert numbers already typed.
Built-up area | 1500 | In the units you chose (sq ft or sq m). Total floor area.
Target budget (₹) | 2500000 | The most you plan to spend
Contingency (%) | 10% | Extra money for unknowns. Added to the estimate.
GST on works (%) | 0% | Leave at 0% until your accountant confirms the rate for your contract.
Start date | 2026-11-01 | Drives the start of the Timeline.
AUTOMATIC CONVERSIONS (do not edit)
Length factor to feet
Area factor to sq ft
Built-up area in sq ft

## Room Area
ROOM AREA
Type the size of each room. The areas add up automatically.
EXAMPLE: placeholder rates and quantities. These totals are NOT a real estimate.
Room / space |  |  | Count (identical rooms) | Area (sq m)
Living room | 18 | 14 | 1
Dining | 12 | 10 | 1
Kitchen | 10 | 9 | 1
Master bedroom | 13 | 12 | 1
Bedroom 2 | 12 | 11 | 1
Bedroom 3 | 11 | 10 | 1
Attached toilet 1 | 6 | 5 | 1
Attached toilet 2 | 6 | 5 | 1
Common toilet | 5 | 6 | 1
Passage / utility | 8 | 6 | 1
Foyer | 6 | 6 | 1
TOTAL
Enter up to 12 rooms. Paint & Tiles reads these rooms, so enter them once here.
Tip: for 4 identical bathrooms, type 4 in Count. Count multiplies walls and floor.

## Earthwork
EARTHWORK
Soil to dig for foundations, trenches and pits. Dimensions follow your Units setting.
EXAMPLE: placeholder rates and quantities. These totals are NOT a real estimate.
Item |  |  |  | Count | Volume (cu ft) | Volume (m³)
Foundation trench (outside walls) | 160 | 2 | 3.5 | 1
Foundation trench (inside walls) | 120 | 1.5 | 3.5 | 1
Septic tank pit | 8 | 6 | 6 | 1
TOTAL EXCAVATION (before allowance)
ALLOWANCE
Extra for over-digging and working space (%) | 10%
Total to excavate (cu ft)
Total to excavate (m³)
COST (₹)
Excavation cost (₹)
Not included: backfilling, soil removal by lorry, dewatering and rock. Get a separate quote for soil removal.
Excavation rate is on the Rates tab (row 16). It is a placeholder until you enter your own quote.

## Paint & Tiles
PAINT & TILES
Enter each room once. Paint and tile totals add up all rooms. Dimensions follow your Units setting.
EXAMPLE: placeholder rates and quantities. These totals are NOT a real estimate.
ROOM DATA (walls for paint, floor for tiles)
Room |  |  | Doors (count) | Windows (count) | Notes | Count (from Room Area)
|  | 10 | 1 | 2
|  | 10 | 0 | 1
|  | 10 | 1 | 1
|  | 10 | 1 | 1
|  | 10 | 1 | 1
|  | 10 | 1 | 1
|  | 8 | 1 | 1
|  | 8 | 1 | 0
|  | 8 | 1 | 0
|  | 10 | 0 | 0
|  | 10 | 0 | 0
TOTAL
OPENINGS (standard size, applies to every room)
3
7
4
4
PAINT SETTINGS
Number of coats | 2
Paint coverage (sq ft per litre) | 100
Extra for waste (%) | 10%
TILE SETTINGS
Tile length (mm) | 600
Tile width (mm) | 600
Extra for cutting and breakage (%) | 10%
RESULTS
Net wall area to paint (sq ft)
Litres of paint to buy
Paint cost (₹)
Floor area to tile (sq ft)
Tiles to buy
Tile cost (₹)
Tip: enter a row per room. Leave unused rows blank. Count the openings in each room.
OPENINGS TOTAL (linked to Bricks & Blocks)
Window area, all rooms (sq ft)
Door area, all rooms (sq ft)

## Exterior & Roof
EXTERIOR PAINT & ROOF
Outside walls and a flat roof. Dimensions follow your Units setting. Pitched roofs are not covered here.
EXAMPLE: placeholder rates and quantities. These totals are NOT a real estimate.
EXTERIOR WALLS
160
10
60
Number of coats | 2
Paint coverage (sq ft per litre)
Extra for waste (%)
Litres of exterior paint to buy
Exterior paint cost (₹)
Exterior painting labour (₹)
FLAT ROOF (terrace)
1500
Roof waterproofing cost (₹)
TOTAL
Exterior paint and roof total (₹)
Enter the outside wall length and height. Openings are subtracted. Two coats is a common default. Check with your painter.
Roof: flat roofs only. A sloped roof needs its own quote for sheets or tiles.
The roof rate should cover both material and labour. Use your own quote.
Not included: scaffolding, cleaning, crack repair, and external plaster.

## Concrete
CONCRETE
Enter the size of each concrete item. Mix quantities and cost are worked out for you.
EXAMPLE: placeholder rates and quantities. These totals are NOT a real estimate.
Item |  |  |  | Count | Volume (cu ft) | Volume (m³)
Slab | 30 | 50 | 0.42 | 1
Beams | 150 | 0.75 | 1.25 | 1
Columns | 0.75 | 1 | 10 | 12
Footings | 4 | 4 | 1.5 | 12
TOTAL CONCRETE
MIX RATIO (use the grade your engineer specifies)
Cement parts | 1 | 1 : 2 : 4 is an example mix only. The grade and mix come from your engineer's specification, which always takes priority.
Sand parts | 2
Aggregate parts | 4
Dry volume factor (wet to dry) | 1.54
Dry volume (cu ft)
Total parts
MATERIALS NEEDED (before extra wastage)
Cement bags (50 kg)
Sand (cu ft)
Aggregate (cu ft)
COST (₹)
Cement
Sand
Aggregate
Labour
TOTAL CONCRETE COST

## Bricks & Blocks
BRICKS & BLOCKS
How many bricks or blocks each wall needs.
EXAMPLE: placeholder rates and quantities. These totals are NOT a real estimate.
Wall |  |  | Net area (sq ft) | Thickness (mm) | Volume (m³)
External walls | 160 | 10 |  | 230
Internal walls | 120 | 10 |  | 115
TOTAL
Openings are linked: windows are taken off external walls, and doors off internal walls. Move any door in an outside wall by hand.
ASSUMPTIONS (change only if your mason or supplier advises)
Bricks per cu m of wall (approximate) | 500
Extra for breakage (%) | 5%
AAC block length (mm) | 600
AAC block height (mm) | 200
AAC block thickness (mm) | 200
RESULTS
Red clay bricks needed (includes breakage)
Brick cost (₹)
AAC blocks needed (alternative to bricks)
AAC block cost (₹)
Masonry labour (₹)
TOTAL MASONRY COST, brick option (₹)
Tip: use bricks or AAC blocks, not both. Mortar is not included.

## Plaster
PLASTER
Cement and sand for plaster on walls and ceilings. Areas come from the Paint & Tiles tab. Assumptions are marked for checking.
EXAMPLE: placeholder rates and quantities. These totals are NOT a real estimate.
AREA (from Paint & Tiles)
Wall area to plaster (sq ft)
Ceiling area to plaster (sq ft)
Total area to plaster (sq ft)
ASSUMPTIONS (confirm with your mason or engineer)
Plaster thickness (mm) | 12
Dry volume factor (wet to dry) | 1.27
Cement parts | 1
Sand parts | 6
Extra for wastage (%) | 10%
RESULTS
Wet volume (cu ft)
Dry volume incl. wastage (cu ft)
Cement bags (50 kg)
Sand (cu ft)
COST (₹)
Cement
Sand
TOTAL PLASTER MATERIAL COST
Plaster labour (₹)
Plaster labour is included at the rate on the Rates tab. Check the rate with your mason.
Wastage is included once here. The Order List does not add more for plaster sand.
Area is the interior wall area from Paint & Tiles plus the floor area as ceilings. External wall faces are NOT included.

## Steel
STEEL
Steel weight from bar size and number of bars. Bar length is always in metres.
EXAMPLE: placeholder rates and quantities. These totals are NOT a real estimate.
Bar diameter (mm) | Length per bar (m) | Number of bars | Weight (kg) | Weight (tonnes)
8 | 12 | 150
10 | 12 | 120
12 | 12 | 100
16 | 12 | 40
20 | 12 | 0
TOTAL
Steel cost (₹)
Tip: weight per metre = diameter² ÷ 162. Check bar lengths against your structural drawings.

## Services
SERVICES
Count the points and fittings, then enter a rate per point. Blank counts or rates show zero.
EXAMPLE: placeholder rates and quantities. These totals are NOT a real estimate.
Item | Count | Rate per item (₹, you enter) | Cost (₹)
Water point for WC | 3 | 2500
Water point for wash basin | 3 | 2500
Shower point | 3 | 2500
Kitchen sink point | 1 | 2500
Washing machine point | 1 | 2500
Overhead tank connection | 1 | 2500
Water heater point | 1 | 2500
PLUMBING TOTAL
Electrical points
Light points | 25 | 1200
Fan points | 6 | 1200
6 A plug points | 20 | 1200
16 A plug points | 8 | 1200
AC points | 3 | 1200
Geyser point | 2 | 1200
TV or data points | 3 | 1200
Distribution board | 1 | 1200
ELECTRICAL TOTAL
Pipes, wires and conduits are included in the rate per point if your rate covers them. Confirm with your plumber or electrician.

## Cost Estimate
COST ESTIMATE
Full estimate. Calculator items fill in automatically. Enter the rest yourself and tag each line with a stage.
EXAMPLE: placeholder rates and quantities. These totals are NOT a real estimate.
Cost item | Source | Estimated (₹) | Actual spent (₹) | Difference (₹) | % of estimate spent | Status | Stage
Site preparation & foundation (excavation, clearing) | Auto |  |  |  |  | Planned | Site preparation & foundation
Concrete & RCC | Auto |  |  |  |  | Planned | Structure (concrete & steel)
Steel reinforcement | Auto |  |  |  |  | Planned | Structure (concrete & steel)
Brickwork & masonry labour | Auto |  |  |  |  | Planned | Masonry (walls)
Plaster (walls and ceilings, materials and labour) | Auto |  |  |  |  | Planned | Masonry (walls)
Floor tiles (materials and laying labour) | Auto |  |  |  |  | Planned | Flooring
Interior paint (materials and labour) | Auto |  |  |  |  | Planned | Painting
External paint (materials and labour) | Auto |  |  |  |  | Planned | Painting
Doors | Enter |  |  |  |  | Planned | Doors, windows & fittings
Windows | Enter |  |  |  |  | Planned | Doors, windows & fittings
Plumbing fittings and pipes | Auto |  |  |  |  | Planned | Plumbing & electrical
Electrical wiring and fittings | Auto |  |  |  |  | Planned | Plumbing & electrical
Kitchen counter and cabinets | Enter |  |  |  |  | Planned | Kitchen & bathrooms
Sanitaryware and taps | Enter |  |  |  |  | Planned | Kitchen & bathrooms
Waterproofing (bathrooms, kitchen, wet areas) | Enter |  |  |  |  | Planned | Kitchen & bathrooms
Roof waterproofing (flat roof) | Auto |  |  |  |  | Planned | Structure (concrete & steel)
General labour (not in calculators) | Enter |  |  |  |  | Planned | Approvals, fees & other
Transport and unloading | Enter |  |  |  |  | Planned | Approvals, fees & other
Approvals and fees (total from Permits tab) | Auto |  |  |  |  | Planned | Approvals, fees & other
Other | Enter |  |  |  |  | Planned | Approvals, fees & other
SUBTOTAL (before contingency and GST)
Contingency
GST on works
TOTAL ESTIMATE
Target budget
Headroom (positive = under budget)
Cost per sq ft (₹)

## Room Costs
ROOM COSTS
Paint and tile cost for each room. Structure, masonry, plumbing and electrical are not assigned to rooms.
EXAMPLE: placeholder rates and quantities. These totals are NOT a real estimate.
Room | Paint cost (₹) | Tile cost (₹) | Paint and tiles (₹) | Share of paint and tiles
TOTAL
Room figures are unrounded estimates. Paint & Tiles rounds up to whole litres and tiles, so the totals can differ slightly.

## Stage Budget
STAGE BUDGET
Costs grouped by build stage. Set a target share for each stage and see where you stand.
EXAMPLE: placeholder rates and quantities. These totals are NOT a real estimate.
Stage | Estimated (₹, before contingency & GST) | Share of estimate | Target share (%) | Target (₹) | Actual spent (₹) | Room left (₹) (+ within target) | Status
Site preparation & foundation |  |  | 8%
Structure (concrete & steel) |  |  | 30%
Masonry (walls) |  |  | 15%
Flooring |  |  | 8%
Painting |  |  | 7%
Doors, windows & fittings |  |  | 7%
Plumbing & electrical |  |  | 12%
Kitchen & bathrooms |  |  | 8%
Approvals, fees & other |  |  | 5%
TOTAL
Target shares should add up to 100%. The shares shown are examples only. Set your own to match your plan.

## Stage Checklist
STAGE CHECKLIST
Checks to do before moving to the next stage. These are general points. Your engineer or site supervisor decides the actual requirements.
EXAMPLE: placeholder rates and quantities. These totals are NOT a real estimate.
Stage | Check before moving on | Done? | Date checked | Who checked | Notes
Site preparation & foundation
Site preparation & foundation | Soil test report received
Site preparation & foundation | Layout marked and checked against the approved plan
Site preparation & foundation | Foundation depth and width inspected before concrete is poured
Structure (concrete & steel)
Structure (concrete & steel) | Steel bar size, spacing and cover match the drawings before concrete
Structure (concrete & steel) | Concrete grade as specified; test cubes taken
Structure (concrete & steel) | Formwork checked for level and alignment
Structure (concrete & steel) | Curing started and recorded
Masonry (walls)
Masonry (walls) | Walls checked for alignment and vertical level
Masonry (walls) | Mortar mix as specified
Masonry (walls) | Lintels or bands in place above openings
Flooring
Flooring | Floor surface level and dry
Flooring | Tile layout planned before fixing
Flooring | Tiles from the same batch
Flooring | Joints checked after fixing
Painting
Painting | Walls fully dry and plastered
Painting | Primer applied
Painting | Number of coats as specified
Painting | Paint batch numbers recorded
Doors, windows & fittings
Doors, windows & fittings | Frames fixed plumb and level
Doors, windows & fittings | Hardware and glass match the order
Doors, windows & fittings | Gaps around frames sealed
Plumbing & electrical
Plumbing & electrical | Water lines pressure-tested
Plumbing & electrical | Electrical circuits and earthing tested
Plumbing & electrical | Concealed work photographed before walls are closed
Kitchen & bathrooms
Kitchen & bathrooms | Waterproofing tested (ponding test) before tiling
Kitchen & bathrooms | Fittings match the order
Kitchen & bathrooms | Drainage tested to flow freely
Approvals, fees & other
Approvals, fees & other | Building approval in hand before work starts
Approvals, fees & other | Completion certificate requested
Approvals, fees & other | Final payment made only after final inspection
Keep photos and signed records of each check. They show what was checked and when.

## Order List
ORDER LIST
What to buy, how much, from whom, and by when. Quantities come from the calculators.
EXAMPLE: placeholder rates and quantities. These totals are NOT a real estimate.
Material | Stage | Unit | Calculated quantity | Extra for wastage (%) | Order quantity | Unit rate (₹) | Line cost (₹) | Supplier | Order by | Ordered? | Received?
Cement (50 kg bag) | Structure (concrete & steel) | bags |  | 0%
M-sand | Structure (concrete & steel) | cu ft |  | 10%
20 mm aggregate | Structure (concrete & steel) | cu ft |  | 5%
TMT steel 8 mm | Structure (concrete & steel) | kg |  | 5%
TMT steel 10 mm | Structure (concrete & steel) | kg |  | 5%
TMT steel 12 mm | Structure (concrete & steel) | kg |  | 5%
TMT steel 16 mm | Structure (concrete & steel) | kg |  | 5%
TMT steel 20 mm | Structure (concrete & steel) | kg |  | 5%
Red clay bricks | Masonry (walls) | pieces |  | 0%
Floor tiles | Flooring | tiles |  | 0%
Interior paint | Painting | litres |  | 0%
Cement (plaster) | Masonry (walls) | bags |  | 0%
M-sand (plaster) | Masonry (walls) | cu ft |  | 0%
TOTAL MATERIAL COST
Wastage starts at the defaults shown. Change them to match your supplier's advice.
Bricks and tiles already include their breakage allowance, so no extra wastage is added here.
Use the spare rows for paint primer, sanitary items or anything else you buy. Enter the quantity and rate by hand.
This list covers materials only. Labour, transport and fittings are on the Cost Estimate tab.

## Task Tracker
TASK TRACKER
Every job on the build, who does it, and when it is due. Overdue tasks turn red.
EXAMPLE: placeholder rates and quantities. These totals are NOT a real estimate.
Task | Stage | Room / area | Assigned to | Start date | Due date | Priority | Status | Days left | STATUS SUMMARY
Get building approval |  | General | Owner |  |  | High | Not started |  | Not started
Soil test |  | General | Soil tester |  |  | High | Not started |  | In progress
Mark layout on site |  | General | Engineer / mason |  |  | High | Not started |  | Done
Order cement and steel |  | General | Owner |  |  | High | Not started |  | On hold
Steel bar check before concrete |  | General | Engineer |  |  | High | Not started |  | Overdue (not Done)
Brickwork to lintel level |  | General | Mason |  |  | Medium | Not started
Plumbing lines in walls |  | Bathrooms | Plumber |  |  | Medium | Not started
Electrical conduits in walls |  | General | Electrician |  |  | Medium | Not started
Waterproofing test |  | Bathrooms | Waterproofing contractor |  |  | High | Not started
Order floor tiles |  | General | Owner |  |  | Medium | Not started
Paint primer coat |  | General | Painter |  |  | Low | Not started
Final inspection |  | General | Engineer |  |  | High | Not started
Overdue = due date has passed and the task is not Done. Days left is counted from today.
Pre-filled tasks are examples. Change or delete them to suit your build.
Formulas:
Days left = IF([Due date]="","",[Due date]-TODAY())

## Permits
PERMITS & APPROVALS
Track each approval your build needs. Which ones apply depends on your city and project. Check with your local authority.
EXAMPLE: placeholder rates and quantities. These totals are NOT a real estimate.
Approval / permit | Who issues it | Needed for your project? | Applied on | Approved on | Status | Reference number | Notes | Fee (₹)
Building plan approval | Local development / planning authority | Check |  |  | Not applied |  |  | 10000
Building permit or commencement certificate | Local development / planning authority | Check |  |  | Not applied |  |  | 0
Structural engineer's certificate | Licensed structural engineer | Check |  |  | Not applied |  |  | 15000
Soil test report | Accredited soil testing lab | Check |  |  | Not applied |  |  | 6000
Water connection | Local water supply authority | Check |  |  | Not applied
Sewer connection | Local sewerage authority | Check |  |  | Not applied
Temporary electricity connection | Electricity distribution company | Check |  |  | Not applied
Permanent electricity connection | Electricity distribution company | Check |  |  | Not applied
Occupancy / completion certificate | Local development / planning authority | Check |  |  | Not applied
Property tax registration | Local municipal body | Check |  |  | Not applied
TOTAL FEES AND APPROVAL COSTS
Check with your engineer and local authority which approvals must come before work starts. Local rules decide the order.
These are the usual approvals, not a legal list. Your local authority decides what applies to your plot.

## Rates
RATES
Type in your local rates. Blank rates show zero cost until you enter them.
EXAMPLE: placeholder rates and quantities. These totals are NOT a real estimate.
Item | Unit | Your rate (₹) | Supplier / source | Date updated
Cement | per 50 kg bag | 600 | Sample figure, not a quote
M-sand | per cu ft | 60 | Sample figure, not a quote
20 mm aggregate | per cu ft | 70 | Sample figure, not a quote
Red clay brick | per piece | 9 | Sample figure, not a quote
AAC block | per piece | 80 | Sample figure, not a quote
TMT steel | per kg | 75 | Sample figure, not a quote
Interior paint | per litre | 350 | Sample figure, not a quote
Floor tile | per sq ft | 40 | Sample figure, not a quote
Concrete labour | per cu ft | 50 | Sample figure, not a quote
Masonry labour | per sq ft | 120 | Sample figure, not a quote
Excavation | per cu ft | 35 | Sample figure, not a quote
Exterior paint | per litre | 350 | Sample figure, not a quote
Roof waterproofing, material and labour | per sq ft of roof | 45 | Sample figure, not a quote
Plaster labour | per sq ft of plaster | 12 | Sample figure, not a quote
Painting labour | per sq ft of wall | 8 | Sample figure, not a quote
Tile laying labour | per sq ft of floor | 10 | Sample figure, not a quote
Tip: get quotes from at least two suppliers. The Rate Library can store them.
EXAMPLE FILE: every rate above is a placeholder to show how the file works. Replace all of them with your own quotes.

## Rate Quotes
RATE QUOTES
Compare two supplier quotes for each item. Only compare quotes that cover the same delivery and loading terms.
EXAMPLE: placeholder rates and quantities. These totals are NOT a real estimate.
Item | Unit (as on Rates tab) | Supplier A | Rate A (₹) | A includes delivery and loading? (Yes/No) | Supplier B | Rate B (₹) | B includes delivery and loading? (Yes/No) | Lower rate, same terms (₹)
Cement | per 50 kg bag
M-sand | per cu ft
20 mm aggregate | per cu ft
Red clay brick | per piece
AAC block | per piece
TMT steel | per kg
Interior paint | per litre
Floor tile | per sq ft
Concrete labour | per cu ft
Masonry labour | per sq ft
Excavation | per cu ft
Exterior paint | per litre
Roof waterproofing, material and labour | per sq ft of roof
Plaster labour | per sq ft of plaster
Painting labour | per sq ft of wall
Tile laying labour | per sq ft of floor
Copy the lower rate from column I to the Rates tab, and record the supplier and date there.

## Assumptions
ASSUMPTIONS
Every factor the calculations use. Change the value on the tab shown. Source status must be confirmed before you rely on a figure.
EXAMPLE: placeholder rates and quantities. These totals are NOT a real estimate.
Factor | Current value | Unit | Where to change it | Source status | Verified value (engineer fills) | Verified by | Source reference | Date verified
Contingency |  | % | Setup | Your choice. Set by you.
GST on works |  | % | Setup | NOT VERIFIED. Confirm the rate for your contract with your accountant.
Dry volume factor (wet to dry concrete) |  | x | Concrete | Common practice. Not sourced. Engineer to confirm.
Cement parts (mix) |  | parts | Concrete | Example mix only. Use your engineer's grade and mix.
Sand parts (mix) |  | parts | Concrete | Example mix only. Use your engineer's grade and mix.
Aggregate parts (mix) |  | parts | Concrete | Example mix only. Use your engineer's grade and mix.
Cement bag volume (1.25 cu ft per 50 kg bag) | 1.25 | cu ft | This tab (row 11) | Practice. Not sourced. Supplier to confirm.
Bricks per cu m of wall |  | pieces | Bricks & Blocks | Approximation. Not sourced. Mason to confirm.
Brick breakage allowance |  | % | Bricks & Blocks | Practice. Not sourced.
Paint coverage |  | sq ft per litre | Paint & Tiles | Assumption. Check the coverage on the paint label.
Paint waste allowance |  | % | Paint & Tiles | Practice. Not sourced.
Number of coats |  | coats | Paint & Tiles | Your choice. Check with the painter.
Standard door size (width) |  | units | Paint & Tiles | Assumption. Measure your doors.
Standard window size (width) |  | units | Paint & Tiles | Assumption. Measure your windows.
Tile size (length) |  | mm | Paint & Tiles | Assumption. Use your tile's size.
Tile cutting and breakage allowance |  | % | Paint & Tiles | Practice. Not sourced.
Steel weight constant (diameter² ÷ 162) | 162 | kg per m | This tab (row 21) | Unit-weight formula for TMT bars. Engineer to confirm against IS 1786.
Plaster thickness |  | mm | Plaster | Practice. Not sourced.
Plaster mix (cement : sand) |  | parts | Plaster | Practice. Not sourced.
Plaster dry volume factor |  | x | Plaster | Practice. Not sourced.
Plaster waste allowance |  | % | Plaster | Practice. Not sourced.
Excavation over-digging allowance |  | % | Earthwork | Practice. Not sourced.
Wastage on sand (Order List) |  | % | Order List | Practice. Not sourced. Supplier to confirm.
Wastage on aggregate and steel (Order List) |  | % | Order List | Practice. Not sourced. Supplier to confirm.
Bill check tolerance |  | % | Bill Check | Your choice.
Quotation valid for |  | days | Quotation | Your choice. Check local practice.
Stage target shares | Stage Budget column D | % | Stage Budget | Examples only. Set your own.
Conversion factors (ft to m, sq ft to sq m, cu ft to cu m, mm to ft) | 3.28084 / 10.7639 / 35.3147 / 304.8 | - | Fixed in formula | Exact unit conversions.
Nothing on this tab is a source. Each line says whether it has been checked. Until it is, treat the figure as an estimate.
Engineer or quantity surveyor: fill columns F to I for each factor you confirm. Leave blank any factor you cannot confirm.

## Terms & Disclaimer
TERMS & DISCLAIMER
Read before relying on any figure in this file.
EXAMPLE: placeholder rates and quantities. These totals are NOT a real estimate.
What this file is | A planning tool. It calculates quantities and costs from the measurements, rates and assumptions you enter.
What this file is not | It is not a structural design. It does not check loads, safety or building bylaws. It does not replace a structural engineer, architect, quantity surveyor or licensed contractor.
Estimates only | Results depend on your measurements, your rates and the assumptions on the Assumptions tab. Rates are blank or placeholders until you enter your own.
Sample figures | The EXAMPLE file's rates and quantities are placeholders. Do not use them as market prices or as a benchmark for cost per sq ft.
Not professional advice | This is not legal, tax, financial or building advice. Confirm GST, approvals and contract terms with your accountant, lawyer and local authority.
Testing | The formulas were checked in LibreOffice. They have not yet been checked in Microsoft Excel or Google Sheets. Check the figures yourself before you buy or pay.
Your responsibility | You decide what to buy, pay for, and build. Check every quantity and rate before you act on it.
TO COMPLETE BEFORE SALE | [Support contact]. [Update policy]. [Refund policy]. [Licence to use]. [Seller name and address]. These are not written yet.

## Dashboard
DASHBOARD
Your project at a glance. Everything here updates as you change the other tabs.
EXAMPLE: placeholder rates and quantities. These totals are NOT a real estimate.
PROJECT
Project
Location
Built-up area
Target budget (₹)
MONEY
Estimated total (₹)
Actual spent (₹)
Headroom vs target (₹)
Cost per sq ft (₹)
Spent so far (% of estimate)
MATERIALS
Paint to buy (litres)
Floor tiles to buy
Bricks needed
Cement bags (50 kg)
Steel (tonnes)
Concrete (cu ft)
Material cost from Order List (₹)
Actual-spend bars stay empty until you enter actual spend on the Cost Estimate tab.

## Bill Check
BILL CHECK
Compare the quantities a contractor claims with the quantities this file calculates.
EXAMPLE: placeholder rates and quantities. These totals are NOT a real estimate.
Allowed difference before flagging (%) | 5%
Item | Unit | Our calculation | Contractor's claim | Difference | Difference % | Result
Room area | sq ft
Concrete volume | cu ft
Brickwork net area | sq ft
Paint (litres) | litres
Floor tiles | tiles
Bricks | pieces
Cement bags | bags
Steel | kg
A higher claim is not always wrong. Check first whether the contractor included wastage, a different unit or a different room.
Compare like with like: the same units, the same rooms, and the same wastage allowance.

## Projects
PROJECTS
Track up to five projects in one file. Enter each project's totals here.
EXAMPLE: placeholder rates and quantities. These totals are NOT a real estimate.
Project | City | Budget (₹) | Estimate (₹) | Spent so far (₹) | % spent | Status
TOTAL

## Bids
BIDS
Compare up to three contractor quotes for each job. The lowest bid is picked automatically.
EXAMPLE: placeholder rates and quantities. These totals are NOT a real estimate.
Job | Contractor 1 | Bid 1 (₹) | Contractor 2 | Bid 2 (₹) | Contractor 3 | Bid 3 (₹) | Lowest bid (₹) | Lowest bidder | Saving vs highest bid (₹)
Civil work
Electrical
Plumbing
Painting
Tiling
Carpentry
Kitchen
Labour
Other
TOTAL
Add the same job from each contractor on one row. Blank bids are ignored.

## Payments
PAYMENTS
Record what you've paid and any changes to the contract. See the balance still to pay.
EXAMPLE: placeholder rates and quantities. These totals are NOT a real estimate.
PAYMENTS MADE | [5 empty] | SUMMARY
Date | Paid to | What for | Amount (₹) | Payment type | Notes | Estimated total (₹)
Approved changes (₹)
Revised forecast (₹)
Total paid (₹)
Balance still to pay (₹)
Deposits paid (₹)
[6 empty] | Changes paid from contingency? (Yes/No) | No
TOTAL PAID
CHANGE ORDERS (extra work or savings agreed after the contract)
Date | Description | Amount (₹) (+ extra / - saving) | Approved?
APPROVED CHANGES

## Timeline
TIMELINE
Plan your stages, track progress and see how many days are left. Dates start from the Setup start date.
EXAMPLE: placeholder rates and quantities. These totals are NOT a real estimate.
Phase / task | Start date | End date | Days | Status | Progress (%) | Days left
Design & approvals |  |  |  | Not started | 0%
Site preparation |  |  |  | Not started | 0%
Foundation |  |  |  | Not started | 0%
Structure (columns & beams) |  |  |  | Not started | 0%
Brickwork |  |  |  | Not started | 0%
Plumbing & electrical |  |  |  | Not started | 0%
Plastering |  |  |  | Not started | 0%
Flooring |  |  |  | Not started | 0%
Painting |  |  |  | Not started | 0%
Fixtures & finishing |  |  |  | Not started | 0%
Handover |  |  |  | Not started | 0%
Dates are formulas from the Setup start date. Type over them to set your own dates.
Durations and task names are placeholders. Adjust them to your build before you rely on the dates.
Formulas:
Days left = IF([End date]="","",[End date]-TODAY())

## Quotation
QUOTATION
Print-ready estimate for your client. Fill in your details and print or save as PDF.
EXAMPLE: placeholder rates and quantities. These totals are NOT a real estimate.
From (your company) | Your company name
To (client)
Project
Location
Date
No. | Item | Amount (₹)
1
2
3
4
5
6
7
8
9
10
11
12
13
14
15
16
17
18
19
20
Subtotal
Contingency
GST
TOTAL
Terms | Quotation valid for (days) | 30
Quantities are estimates. Final billing is based on measured work. Confirm the GST rate before sending. The file default of 0% is a placeholder.

## Rate Library
RATE LIBRARY
Keep rates from different suppliers and cities. Copy the chosen rate to the Rates tab.
EXAMPLE: placeholder rates and quantities. These totals are NOT a real estimate.
Item | Unit | City | Supplier | Rate (₹) | Date updated | Notes